# Learning Technologies Planning

Getting Started
Step by Step Planning Guide
Sample Learning Technologies Plan Structure

This chapter provides a step by step guide to assist schools in the development of a Learning Technologies (LT) Plan. LT plans that help schools to use ICT effectively include all of the following ten steps (adapted from Successful K-12 Technology Planning: Ten Essential Elements)

The 10 steps are:

- Develop a Vision

- Involve All Stakeholders

- Analyse the Current Situation

- Review the Research

- Integration of ICT into the Curriculum

- Commit to Professional Learning

- Ensure a Sound Infrastructure

- Allocate Appropriate Funding and Budget

- Plan for Ongoing Monitoring and Evaluation

- Prepare for Tomorrow

School LT Plans should be devised as a result of auditing current practice in ICT and identifying priorities for development. Plans should have clear, agreed aims and objectives that describe the school's vision for ICT. The plan should have a timescale, be costed, show responsibilities and be evaluated. Targets should be specific, measurable, achievable, realistic and timed (BECTA)

A school LT Plan should be:
credible, by:

- being an integral part of the school development plan

- building on current ICT use

- linking to school and system goals

manageable, by:

- involving senior staff

- having an impact on individual curriculum planning

- being linked to pupil assessment and attainment

- accepting resource, staffing and budget limitations

sustainable, by:

- gaining the support of all stakeholders: teachers, senior staff, school board, parents and non-teaching staff

- being integrated into financial planning and budgeting procedures

- building in continuing professional learning of staff

- including mechanisms to monitor impact and value for money.

## Getting Started

Whether your school is about to expand or consolidate its current use of ICT, you will need assistance from a planning, implementation and consultation team at every stage of the process, starting with input into and feedback on the vision statement.

School LT Plan team members should include those teachers and leaders who will drive the plan within the school. These are the champions. They may include the ICT Coordinator and committed teachers who will convince others, model effective practice and help drive the change.

The LT Plan team should contain representatives from the following areas:

- School executive

- Curriculum committee

- School Board

- Staff

- Student Representative Council

- Community

## Step by Step Planning Guide

Step 1 - Develop a Vision
Vision is the first step for technology planning. The school must have a picture of what a technology-enhanced program will look like in three to five years. Vision statements are compelling stories that describe how students will be using the technology and how teachers and other staff will be using it for data-driven decision making, increased productivity, and planning. A vision also includes how the learning environment will be enhanced to support technology use.

The following are sample vision statements:

School A:
A Vision for Technology

We envision using technology to further a learning community where:

- Students are engaged in a challenging curriculum that is focused on inquiry based, hands-on learning. Students are comfortable using technology. Students take responsibility for their own educational success.

- Teachers use technology to support all learning across the curriculum. They function as coaches, mentors, advocates, and managers of information. Through ongoing, comprehensive professional development, all teachers acquire the knowledge and skills to integrate technology into a challenging and interdisciplinary curriculum that addresses students' specific needs, developmental levels, and learning styles.

- Administrative functions, including those performed by teaching staff, are fully automated, thereby allowing more of the school system's energy and resources to be focused on student education.

The school becomes an environment where all students and staff have ready access to a full range of current technology, software tools, and applications. The school has knowledgeable staff and external resources (such as parents, community members, business, higher education, and network resources) to further the curriculum goals.

School B:
Vision for Learning Technology

Technology offers students an avenue to succeed as citizens in a global society in which information is growing at an incredible rate. Technology can improve communication, enhance thinking skills, make instruction more efficient and effective, and develop life skills critical to success. School B will incorporate technology as a means of integrating curriculum across subject areas. Students and educators will be guaranteed opportunities to use technology as an integral part of education. In support of this vision, School B offers its Strategic Learning Technology Plan.

Step 2 - Involve All Stakeholders
For any plan to be effective, all stakeholders should have the opportunity to have an input into the goals of the plan. Teachers, administrators, parents, and the wider school community all have a stake in the educational outcomes of students. This involvement can be achieved through the creation of a representative LT Plan team as described above. Ensure that all stakeholders are kept informed and involved in the development and implementation of the school LT plan.

Step 3 - Analyse the Current Situation
You must understand where you are in order to plan for the future, so gather as much data as possible including:

- an audit of professional learning needs: see Appendix A (148kb)

- a schematic diagram of current network structure (both logical and physical)

- an inventory of hardware and software

- information about where hardware and software is deployed

- an audit of current ICT curriculum use in the school to determine areas of need

- an outline of achievements to date and possible areas for development and/or improvement

There are multiple ways to collect the information needed to inform a school LT Plan:

- Use the DET Plan Levels of Effective Use of Learning Technologies and/or the Whole School Development Matrix.

- Survey staff and student use by asking about both their skill levels and how teachers and students are using the technology. Develop your own survey or adapt one developed by another school. See Appendix A for a sample survey for gathering teacher data in relation to professional learning.

Conduct site visits and talk to colleagues from other schools. It may be desirable to visit schools that demonstrate compelling reasons for using technology. This is particularly important if your school uses computers mainly for word processing and drill and practice. If your planning team has never seen student use of multimedia, digital video, or student web pages, it will be difficult for them to envision these uses. Visits can help to open one’s mind to the possibilities.

Step 4 - Review the Research
Knowing what the research says about the use of technology is important to guide your technology planning efforts. Research has found that some technology use impacts student learning while others make no difference (Dwyer 1994; Butzin 2001). The research on technology's effectiveness is divided into two areas: (1) learning with computers, using computers as tutors (most often drill and practice) and (2) learning from computers, which is when the student uses the computer as a tool in the learning process for communication, collaboration, research, or publishing.

A summary of the research finds that technology can impact student learning when the following conditions are evident:

- students have easy access to the technology.

- technology is in the classroom, where it can make a greater impact than when it is in labs.

- ongoing teacher professional learning is provided.

- reform of teaching practices is evident, with a balance between teacher-centred strategies and that of construction, characterised by the teacher serving as a guide and facilitator.

- the software is well matched with the teacher's assessment of student needs and the learning outcomes of the curriculum.

Step 5 - Integration of ICT into the Curriculum
As the research demonstrates, technology impacts student learning when there is a match between student learning outcomes and the technology being used. Teachers face six barriers to effectively integrating technology with their curriculum. The following need to be addressed in your school LT plan:

| Leadership | the lack of leadership is the single biggest barrier to the use of technology. See what the research says |
| --- | --- |
| Access | one or two computers or a weekly visit to a computer lab do not impact student learning. A recommended ratio is 1 computer to every 4/5 students with computers located in every classroom. |
| Time | it takes time for teachers to review software and work out how it fits with their teaching program. |
| Cost | schools often provide only minimal funds to purchase software. |
| Training | a concerted and coordinated professional learning program is essential. Apple Classroom of Tomorrow (ACOT) research found that it takes significant professional learning for teachers to move from “How do I turn it on?” to where they comfortably and routinely integrate technology into their classroom. |
| Reform | technology makes its greatest impact when teachers use inquiry/project-based learning practices to engage students. See ICT, Pedagogy and Learning Environments for further information. |

Implications for your school LT plan:

- the plan needs a commitment from and active support of the school leadership team

- as far as the budget can permit, ICT hardware resources need to be located in classrooms. Each classroom needs a large display facility.

- teachers must be given time to explore, learn and reflect on their practice

- the budget must allow for adequate expenditure on software and professional learning

- teachers must be encouraged and supported to engage in appropriate professional learning

- serious consideration needs to be given to appropriate pedagogies and teaching strategies which facilitate the integration of ICT into teaching and learning. See ICT, Pedagogy and Learning Environments for further information.

Integration of ICT into the Curriculum
The Victorian Curriculum and Assessment Authority have developed a useful set of charts (one for each KLA) which provide a matrix of using ICT to help students achieve CSF learning outcomes from levels 1 to 6 (years K to 10). The charts may be of assistance to schools to see how ICT use can be integrated into the curriculum. They are available for downloading from the Victorian Curriculum and Assessment Authority Website

Student ICT Competencies
Student ICT competencies embedded within teaching/learning projects can help teachers to know which ICT skills students need to demonstrate. The ACT DEYFS ICT Competencies are mandated for assessment in year 10. For further information about the year 10 ICT Competencies go to the DET website.

The NSW Department of Education have developed a set of computer skills for assessment at year 6 and year 10 – details are at http://www.schools.nsw.edu.au/learning/k-6assessments/compskills.php and http://www.boardofstudies.nsw.edu.au/syllabus_sc/computingskills_assessment.html respectively. The NETS project in the U.S. offers another model for all years of schooling.

Step 6 - Commit to Professional Learning
The plan must address goals for professional learning. Providing appropriate training is the key to effective use. Research has demonstrated time and again that an ongoing professional learning program is required (Dwyer 1994; Ringstaff et al. 1991; Ringstaff 2001). The most effective staff development programs deliver to teachers when they need it, at their school, and on their own equipment. One-time "spray and pray" workshops often do not result in any change in teacher behaviour. See Professional Learning for more details.

Ascertaining staff professional learning needs is an integral part of developing a school learning technologies plan. Appendix A provides a sample staff survey in relation professional learning.

See Professional Learning for information about the nature of effective professional learning and professional learning opportunities available through the Centre for Teaching and Learning Technologies.

Teacher ICT Skills
The plan should also address the ICT skills that teachers will be expected to demonstrate. The NETS Project, is one source for teacher ICT skills. Another is the International Computer Driver’s Licence (ICDL) for which the Department has licenced ACT government school teachers to access. Assessment for the ICDL is available from a number of commercial organisations, however Erindale College offers assessment on a cost recovery basis – contact Marion McIntosh, phone 62058104, email marion.mcintosh@erindalec.act.edu.au.

Step 7 - Ensure a Sound Infrastructure 
For ICT to impact student learning, the Learning Technologies Plan must ensure that appropriate resources are in place to support and maintain networks and equipment. Technical support is also essential so that all systems work all the time. Technophobic teachers will quickly give up on technology use when it doesn’t work after they have spent many hours learning about the software and planning technology-enhanced lessons.

Setting standards for software, hardware, networks, and video equipment is crucial. Doing so will result in significant savings in staff development and support costs, including repairs, and will make it easier to upgrade and support school/system licenses. Technical support may be a nightmare otherwise, because incompatible systems can’t “talk” to each other.

In planning for infrastructure the bottom line is that it needs to be reliable, modern and strategically located within the school. School infrastructure needs to be an enabler for the integration of ICT into teaching and learning, not a barrier.

See Managing ICT Infrastructure and Networks, Hardware and Software for information about computer networks and technical support.

Step 8 - Allocate Appropriate Funding and Budget 
The plan should be in line with your school’s financial resources. It should not promise more than the budget can deliver. Research and experience indicates that between 4% and 7% of the total school budget needs to be allocated to ICT capital and recurrent expenditure.

There are two parts to an ICT budget. A recommended formula for the first part is as follows: 40% of every dollar allocated should be for hardware, 20% for software, 20% for professional learning, and 20% for upgrades and additional needs as teachers’ expertise grows. If you spend all of the money on hardware, you will not see the return on student learning because there will be no funds for professional learning, upgrades, and so on. These recommendations are not just for the first year, but for anytime you budget or receive one-time grant dollars.

The second part is a budget for technical support expenses. Support must be available so that teachers have confidence that the time they spend in reviewing software and planning will not be lost when equipment and networks fail to work

A thoughtful learning technologies plan will not consider the purchase of more hardware and networks than the school can maintain with its technical support capacity.

Step 9 - Plan for Ongoing Monitoring and Evaluation 
The plan must address ongoing monitoring and evaluation. Plan to collect data using anecdotal evidence, student artifacts, surveys and tests. Develop benchmarks (minimum outcomes), timelines and roles and responsibilities for all components of the plan. Some questions the evaluation should address are:

- have the goals of the LT Plan been met? If not, why not? What needs to be changed to achieve the goal?

- What elements are missing?

- What needs to be added? Changes for the future?

The LT Plan should address how the results of this evaluation will be communicated to all stakeholders.

Some resources to assist in evaluation process include:
http://www.sofweb.vic.edu.au/lt/pguide/imprev/imprev.htm 
(Department of Education, Victoria)

http://www.discover.tased.edu.au/ec/leaders/index.htm and click on ‘School Planning for ICT’ (Department of Education, Tasmania)

http://www.wested.org/techplan/pdfs/IMPASSM.PDF

http://www.edgateway.net/cs/tk/print/rtec_docs/monitoring.html

http://www.apple.com/education/planning/evaluate/index.html

Step 10 - Prepare for Tomorrow 
While planning for today, keep an eye on tomorrow by allowing for new and promising practices and technologies. Remember back ten years ago when “www” didn’t mean the World Wide Web, laptop computers were big and called “luggables” by those who owned them, and when 48k and a 24-baud modem were fast?

Would you have predicted back then the hardware, networks, and software you have in your schools now? Probably not. Ten years from now will computers even look like the computers we use now? How will Personal Digital Assistants (PDAs) and other handhelds change the way we organise and learn? And, finally will we all be totally wireless, able to communicate at anytime, anywhere?

In preparation for the future, set some funds aside to encourage teachers to try new applications and determine what value, if any, these applications have for your program before you purchase items only a “techie” could love.

ICT can improve teaching and learning when a school develops a plan that incorporates these essential elements and provides appropriate funding to make its vision a reality.

## Sample Learning Technology Plan Structure

A sample Learning Technologies Plan Structure (22kb) is available for download.

References

Butzin, Sarah M. (2001). Using instructional technology in transformed learning environments: An evaluation of Project CHILD. Journal of Research on Technology in Education 33 (4): 367-73.

Dwyer, David. (1994). Apple classrooms of tomorrow: What we’ve learned. Educational Leadership 51 (7): 4-10. (EJ508281)

Dwyer, D.C., C. Ringstaff, & J.H. Sandholtz. (1991). Changes in teachers’ beliefs and practices in technology-rich classrooms. Educational Leadership 48 (8): 45-52. (EJ425608)

Kulik, J.A. (1994). Meta-analytic studies on computer-based instruction in E. Baker and H. O’Neil, eds., Technology assessment in education and training. Hillsdale, NJ: Lawrence Erlbaum Associates.

Mann, D., C. Shakeshaft, J. Becker, and R. Kottkamp. (1999). Achievement gains from a statewide comprehensive instructional technology program. Charleston: West Virginia State Department of Education. (ED429575)

Ringstaff, C. (November 2001). The learning return on your educational technology investment: A survey of recent research findings. WestEd. Available online

Other Planning Resources

Victorian Department of Education and Training 
An extensive online guide to assist schools in planning for the effective integration of ICT into teaching and learning.

http://www.tdd.nsw.edu.au/tilt/planning/index.htm 
A five step guide for the development of a school learning technologies plan.

British Educational Communications and Technology Agency (BECTA) 
What makes a good ICT development plan.

Apple Classrooms of Tomorrow (ACOT) 
ACOT was a research and development collaboration among public schools, universities, research agencies, and Apple Computer, Inc. Initiated in 1985, ACOT began its work in seven classrooms that represented a cross-section of Americas elementary and secondary schools. Its goal was to study how the routine use of technology by teachers and students might change teaching and learning.

Apple Technology Planning Guide 
The Planning Guide is a tool designed to assist you in creating and implementing a technology integration plan for your school or district.

Technology Planning Toolkit 
Provides rubrics, checklists, and other guides for planning technology implementation. Where appropriate, links are provided to other sites that offer models of best practice, example plans, and additional tools and resources to support a more informed technology planning program.

The Guiding Questions for Technology Planning 
Designed to help begin a technology planning process, select a planning model, and move the process forward. It is considered most useful when it is used within a larger planning process and not simply as an add-on or one-time discussion.